## Sheet1
Test Result Summary
| Overall progress of the QA cycle(Completed, during, stopped) | Completed
| Total number of test cases | 20
| Number of testers | 2
| Test cycle duration | 2 days
Status Update
| Number of test cases planned | 20
| Number of test cases executed | 12
| Number of test cases executed overall | 20-25
| Number of defects encountered | 6
| Number of critical defects | 1
Overall Status Update
| Number of test cases planned | 20
| Number of test cases executed | 12
| Pass % of the defects | 100%
| Defects density | 50%
| Critical defects % | 8.3%
Product Build # | User To Root |  | Description | Logs the logins of users
Platform |  |  | Date 3/17/17
Test ID | Description | Expected Result |  |  | Actual Date | Actual Result (Passed / Failed / Not Tested)
1 | Read in log file (Critical) | Log file read |  |  | 2017-02-28 | Failed
2 | Invalid password | Keep count |  |  | 2017-03-05 | Passed
3 | Invalid password input once | Update count |  |  | 2017-03-05 | Passed
4 | Invalid password input multiple times | Update count & log IP |  |  | 2017-03-05 | Failed
5 | Valid password input | Nothing |  |  | 2017-03-05 | Passed
6 | Label single invalid attempt as benign | Update text table for benign attempts |  |  | 2017-03-10 | Passed
7 | Label multiple invalid attempts suspicious | Update text table for suspicious attempts |  |  | 2017-03-10 | Failed
8 | Improper format for log file | Prompt User and don't accept log |  |  | 2017-03-11 | Passed
9 | Communication between netbeans and sqlite | Netbeans GUI should interact with SQLite |  |  | 2017-03-12 | Failed
10 | Highlight suspicious logins | Netbeans text table highlight |  |  | 2017-03-12 | Failed
11 | Netbeans dynamically updating database | Lists logs attempts dynamically |  |  | 2017-03-12 | Failed
12 | Universal log file location | Log file readily accessible |  |  | 2017-03-12 | Passed